## All
| Issue Location | Issue Description | Potential Fix | Status | Notes
1 | iOS audio | audio doesn't work on iOS | polyfill... Fixes are available online
2 | app menus | no home button available to exit apps | copy over the 'exit btn' available on startup to some corner of the app | FIXED | Solution up and running, though currently only implemented in the number fluency app
3 | go home menu pause screen | blur is no strong enough to obscure what is on page, so answer can be searched for without time elapsing | create new FX class 'strong-blur' and use it in these situations | FIXED | very strong blur
4 | pause button | currently no way to directly pause when doing an activity (indirect pausing can be done using the go home button | add an icon that activates the 'pause' functionality developed for the go home feature | FIXED
5 | score recording | score is recorded even if the user quits in the middle of a round | the score should only be recorded if the final display container has appeared (e.g. the time is up or they have 'struck out' in a fluency activity
6 | app start screens | exit button remains if start button pressed too quickly | adjust timing of 'no-touch' class removal on app startup |  | tried to fix it, but it may not be a timing issue?? Or the timing is wrong in another way
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Main Screen
| Issue Location | Issue Description | Potential Fix | Status | Notes
1 | main screen | back button persists in locations where it shouldn't, like on the main menu | take a look at the back button code and how the 'isMainMenu' variable is being changed | FIXED | FINALLY!!!
2 | top container | sub-menu title persists in top container upon return to main menu from a sub-menu or app | check content of menu toggle function…? | FIXED | the sub-menu titles were displaying directly into the top-container, leaving no room for the divs for the username and userscore
3 | back button | looks amateurish | replace with an icon from font-awesome or write 'Back' or both | FIXED | sorta fixed…
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Alphabet - Card Touch
| Issue Location | Issue Description | Potential Fix | Status | Notes
1 | repeat button | not working | probably an orphaned div | FIXED | was an orphaned div
2 | home btn | weird movement when exiting app from home btn | no clue…
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Alphabet - Letter Matching
| Issue Location | Issue Description | Potential Fix | Status | Notes
1 | dots | a once incorrectly matched dot does not behave properly thereafter | no clue | FIXED | Remade the system with separate objects for start and end dots. Also implemented a hybrid observer-mediator pattern to keep track of the changes.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Numbers - 1-20 Touch
| Issue Location | Issue Description | Potential Fix | Status | Notes
1 | new round | no functionality specified as yet; when 'one more time' is selected, another identical grid is added onto the bottom of the first grid | Set up sessions and rounds specific to fluency activities. For new sessions, the grid only needs to be created when the app is first opened, not on each successive play through For rounds, the number of items presented needs to increase with each round. The variable 'round' already exists, and the code for increasing the round number does as well. | FIXED
2 | wrong answer penalty | losing points for wrong answers | have only a sound to indicate a wrong answer | FIXED
3 | rounds and speed | a constant speed should be kept throughout each round; that will help it feel more like a bump to be able to continue, you can't miss more than 5 total? | need to rearrange the rounds and the array generator | FIXED
4 | round change notification | it's hard to know when the round has changed | A more noticeable visible alert should do the trick, such as adding a 'wobble' effect to the round display. A more intensive alternative would be displaying an actual animated banner. | FIXED | for now just added an effect on the round display
5 | number of wrong answers display | overlaps the number buttons | need to fix the heights and positions of the different elements | FIXED | mostly taken care of… still need to be able to have responive design for vertical heights too…
6 | 2nd chances | needed extra incentive to strive for the end of a round | deletion of one of the '×' at the end of the round can provide this | FIXED | clearing a round will now result in deletion of one of the '×' in the answer display however, they should probably be changed to hearts, so that users know what they're up against in the beginning?
7 | number buttons | buttons can be pressed multiple times for extra points | add 'no-touch' after a number is pressed, and release it before (is this possible?) the next number is called | FIXED | put 'no-touch' in the answer evaluation function… if it's correct, no further input is allowed 'no-touch' is removed before the next number is read (in the speak interval function)
8 | number speed increments between rounds | speed of numbers being called may still be too fast… | adjust intervals more ideally it should start becoming difficult at round 10 where point values increase
9 | round change | user can sit out entire rounds with no input | minimum requirement of at least 5-6 inputs per round, regardless of accuracy
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Spelling - Touch
| Issue Location | Issue Description | Potential Fix | Status | Notes
1 | letter display | bottoms of hanging letters are hidden behind btn-container3 | center input letters vertically inside 'letter-display' div | FIXED | Played around with the centering, but ultimately added a thin row under the letter-display div to keep it separate from the ui elements beneath it. Also added 'padding-bottom' of 2rem.
2 | letter display | when too many letters are entered, the extra letters create another line in the div, and those letters are then hidden behind the ui elements. The goal is to have only one line, and not allow any input beyond that. | Having tried different solutions in CSS (white-space:no-wrap, text-overflow:ellipsis, etc) it seems that the character limit will have to be determined dynamically, as it needs to depend on the size of the div, which depends on the screen size. This would involve looking up the CURRENT div size and determining the max characters that could fit in there, then 'poping' all the characters over that limit out of the array until the limit is reached. If a user attempts to enter a character beyond that limit, they should get a visual and aural feedback indicating that it's not possible. | FIXED | Found a simpler solution. Apparently I was implementing the 'white-space:nowrap' wrong… I had a dash, 'no-wrap' instead of 'nowrap'. I got rid of the ellipsis though, so it's more clear, and less interesting that the user has gone beyond the bounds of the letter-display.
3 | app screen | vertical spacing is distorted on certain screens or when the viewing space is not full screen |  | FIXED | tried media queries for height, but to no avail seems to be okay for now??
4 | stuck on word | if a word can't be spelled correctly, can't move on to the next word | words should be skipped after a set number (3?) of tries | FIXED
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30